## Sheet1
# | TASK | STATUS
Project Setup & UI Foundation (15 Jun 2026)
1 | Initialize Next.js Project | completed
2 | Configure Tailwind CSS | completed
3 | Create Folder Structure | completed
4 | Global Layout | completed
5 | Navbar | completed
6 | Sidebar | completed
7 | Footer | completed
8 | Typography | completed
9 | Colour System | completed
10 | Reusable Buttons | completed
11 | Inputs | completed
12 | Cards | pending
13 | Modals | pending
14 | Loaders | pending
Authentication Module (Frontend) (16 Jun 2026)
15 | Design Login | completed
16 | Register | pending
17 | Forgot Password UI | pending
18 | Validation | in progress
19 | Protected Layout | pending
20 | JWT Storage Strategy | pending
21 | Loading States | pending
22 | Error Handling | in progress
Dashboard Module (Frontend) (17 Jun 2026)
23 | Create Dashboard Layout | completed
24 | Statistic Cards | completed
25 | Recent Employees Table | in progress
26 | Responsive Widgets | in progress
Employee Management Module (Frontend) (18 Jun 2026)
27 | Employee List Page | pending
28 | Employee Details Page | pending
29 | Add/Edit Employee Form | pending
30 | Delete Confirmation Modal | pending
31 | Profile Image Upload Preview | pending
32 | Empty States | pending
Search, Filter & UX Module (19 Jun 2026)
33 | Search Bar | pending
34 | Department Filters | pending
35 | Status Filters | pending
36 | Date Filters | pending
37 | Pagination UI | pending
38 | Sorting UI | pending
39 | Toast Notifications | pending
40 | Loading States | pending
Backend Setup & Authentication API (22 Jun 2026)
41 | Express Setup | pending
42 | MongoDB Connection | pending
43 | User Model | pending
44 | JWT Auth | pending
45 | Password Hashing | pending
46 | Login/Register/Logout APIs | pending
47 | Middleware | pending
Employee CRUD API (23 Jun 2026)
48 | Employee Schema | pending
49 | Create, Read, Update, Delete APIs | pending
50 | Soft Delete | pending
51 | Restore | pending
52 | Validation Middleware | pending
53 | Image Upload Backend | pending
Advanced APIs (24 Jun 2026)
54 | Search | pending
55 | Filtering | pending
56 | Pagination | pending
57 | Sorting | pending
58 | Dashboard Statistics Endpoints | pending
59 | Centralized Error Handling | pending
Frontend Integration (25 Jun 2026)
60 | Connect frontend with backend APIs | pending
61 | Axios/Fetch Services | pending
62 | Authentication Flow | pending
63 | CRUD Operations | pending
64 | Dashboard Data | pending
65 | Upload Integration | pending
Testing & Deployment Preparation (26 Jun 2026)
66 | Bug Fixing | pending
67 | Responsive Testing | pending
68 | Performance Optimization | pending
69 | README | pending
70 | Environment Setup | pending
71 | Git Cleanup | pending
72 | Deployment to Vercel | pending
73 | Final QA | pending